## Sheet1
CraterStats Python GUI
Team Members:
Evan Palmisano | Caden Tedeschi | Ibrahim Hmood | Alden Smith | Levi Watlington
[5 empty] | Start Week: | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23
Team Member(s) absent from weekly Mentor Meeting:
[5 empty] | Task Description: | Discuss as a team optimal meeting times for the team - mentor meeting | Comment prototype for readability | Draft Software Design Document | Draft Software Design Document | Team Collaborate | Revise Software Design | Research GUI compatibility for mac osx | Fine tune functionalities | Update Design Review 2 Intro | Update Github Readme | Set up Capstone Project for Pip install deliverable | DR3: Requirements/Specs Review | Project Poster: Combine Challenges & Solution Overview points | Get updated poster printed | Fill out Final Demo Document | Final "As-Is" Report: Requirements, Project Timeline, Future Work, and Conclusion
[5 empty] | Assigned Team Member(s): | All | Caden | All | All | All | All | Evan | Evan | Evan | Evan | Evan | Levi | Levi | All | Evan | Levi
[5 empty] | Start Date: | 2024-08-26 | 2024-09-02 | 2024-08-31 | 2024-08-31 | 2024-09-20 | 2024-09-23 | 2024-09-28 | 2024-10-10 | 2024-10-18 | 2024-10-25 | 2024-11-05 | 2024-11-08 | 2024-11-15 | 2024-11-26 | 2024-12-02 | 2024-12-06
[5 empty] | End Date: | 2024-08-30 | 2024-09-03 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-26 | 2024-10-21 | 2024-10-30 | 2024-11-29 | 2024-11-14 | 2024-11-18 | 2024-11-26 | 2024-12-03 | 2024-12-13
[5 empty] | Measureable Outcome: | N/A | Commented prototype file to help wiht readability | Description of software's overall architectural design. | Description of software's overall architectural design. | Collaborate and decide first three funtions to connect from the Crater Stats Library to the GUI Prototype | Implement vahid's suggested changes to document | The GUI wokrs on windows but the directory format is different for mac. In turn directory navigation needs to be added for different OS types. | Go through each function of current GUI and double check to make sure that the function either works properly or is included in the program | Re-present the introduction to improve the flow of talking and to include teacher and mentor in the presentation | Add visual references for a new user to understand how to operate the application. | Add necessary setup.py and and any other files. Then make the project installable from Pypy installer. | Create the Requirements/ Specs portion of the Design Review 3 presentation | Combine the points from the Challenges and Solution Overview sections into points that are presentable enough for our Poster | Send the updated poster for printing services. | Document specific requirements and correlating features to demonstrate during mentor meeting. | Write the sections listed in task description in the "As-Is" document
[5 empty] | Actual Outcome: | Agreed upon meeting time | Commented prototype file to help with readability | N/A | N/A | N/A | F | The current alpha version of the application executes without error on both operating systems | In Progress | Re-presented the first three slides along with an addition for a faculty slide | Separated the setup into a windows specific instruction markdown file in a newly created directory for usability. The homepage's README contains how to operate the application. | Add necessary setup.py and and any other files. Then make the project installable from Pypy installer. | Around 1 minutes worth of content for the given section | Points that clearly have a problem and a solution to that problem. | Print the correct version of the poster. | Applied four demonstrations of specific features and improvements. | The requirements, project timeline, future work, and conclusion sections of the document are written and make sense.
[5 empty] | Current Status: | Completed | Completed | In Progress | Completed | Completed | Completed | Completed | In Progress | Completed | Completed | In Progress | Complete | Completed | Completed | Completed | Completed
[5 empty] | Task Description: | Draft Team Communication Standards Memo | Fork and download git repository if not already possessed | Distribute the software design document work evenly amongst all teammates | Software Design Introduction | Implement first function | Preview upcoming Design Review | Create a shell script such that the application installs and starts with one click | Research and Implement work-around for running the GUI on Linux systems | DR2 Problem statement Final | Software Testing Plan Usability Testing | Capstone Design Poster Key Elements | Add Poster Content | Update website design | Update the Challenges and Resolutions for Capstone Design Presentation | Final Presentation: content revision (req&specs, sched, conclusion) | Final "As-Is" Report: Testing
[5 empty] | Assigned Team Member(s): | All | All | Evan | Ibrahim | TBH | All | Alden | Ibrahim | Alden | Levi & Evan | Evan | Alden | Evan & Caden | Evan | Levi | Evan
[5 empty] | Start Date: | 2024-08-30 | 2024-09-02 | 2024-09-09 | 2024-09-09 | 2024-09-20 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 2024-10-18 | 2024-10-25 | 2024-11-04 | 2024-11-08 | 2024-11-14 | 2024-11-20 | 2024-11-26 | 2024-12-04
[5 empty] | End Date: | 2024-09-06 | 2024-09-06 | 2024-09-11 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-26 | 2024-12-21 | 2024-11-05 | 2024-11-05 | 2024-11-18 | 2024-11-25 | 2024-11-26 | 2024-11-02 | 2024-12-13
[5 empty] | Measureable Outcome: | A one page document explicitly stating standards of communication within the team and between the team and mentor. | Each team member should have access to the current git hub repository | An even amount of work to be assigned to each teammate in order to complete the draft in an efficient manner | Provides a solid view of the requirements and constraints that this implementation must meet | Dependent on collaboration | Get familiar with the design review requirements. | The user runs the shell scripts and the app runs as intended | After implementing work around GUI is fully functional on Linux systems | improve slides to contain more descriptive information | A well written Usability Testing section | Discuss the key features of the software system. Provide highlights that make team's effort valuable to the client. | Now that we have solidified a style we add the content to the content blocks of our poster. | Redesign the website layout for a more readable format and a condensed amount of information. | Update the context of the team's challeneges and resolutions in time for dry run. | Revise the content of the mentioned slides to satisfy the suggestions given by the team mentor | Provide testing plan and results.
[5 empty] | Actual Outcome: | N/A | Repository access is properly updated | Team members picked topics accordingly. | N/A | N/A | Review all neccessary elements required for the design review presentation | The shell script should configure a python environment and allow for uninterrupted execution | In Progress | present the information in a clear and consise manner | 2-3 pages about the Usability Testing | Collaborated with Levi to combine key features with solution overview. | Content added | Work in progress, as of right now the webiste has an updated page layout and css design. Looking to add content now. | Updated the content by including all major challeneges and resolutions along with updating any current ones the team is facing. | The content of the mentioned slides implements our mentor's suggestions for the slides | Go into depth about different types of testing, methods impemented, and results gathered
[5 empty] | Current Status: | In Progress | Completed | Completed | Completed | Cancelled | Upcoming | Completed | In Progress | done | Completed | Completed | Completed | Completed | Completed | Completed | In Progress
[5 empty] | Task Description: | Draft Software Design Document | Draft Team Communication Standards Memo | Software Design Introduction | Software Design Architectural Overview | Implement second function | Revise Task report structure/content | Continue import implementation | Change demo popup to open files if they were already created | Update Design Review 2 Challenges | Separate plot and data file uploads | Edit Software Testing: Intro, Conclusion | Design Review 3 Prototype Review | Add Poster Content | Continue working on making a clickable graph in program | Update Solution Overview | Meet with Trent
[5 empty] | Assigned Team Member(s): | All | All | TBD | Evan | TBH | Evan | Caden | Levi | Evan | Evan | Evan | Caden | Alden | Caden | Ibrahim | All
[5 empty] | Start Date: | 2024-08-30 | 2024-08-30 | 2024-09-09 | 2024-09-09 | 2024-09-20 | 2024-09-24 | 2024-09-27 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-11-05 | 2024-11-11 | 2024-11-08 | 2024-11-18 | 2024-11-28 | 2024-12-10
[5 empty] | End Date: | 2024-09-20 | 2024-09-06 | 2024-09-20 | 2024-09-20 | 2024-09-27 | 9/31 | 2024-10-12 | 2024-10-27 | 2024-10-21 | 2024-10-30 | 2024-11-08 | 2024-11-14 | 2024-11-22 | 2024-12-05 | 2024-12-04 | 2024-12-10
[5 empty] | Measureable Outcome: | Description of software's overall architectural design. | A one page document explicitly stating standards of communication within the team and between the team and mentor. | Provides a solid view of the requirements and constraints that this implementation must meet | Consists of two parts: an architectural diagram of your system's high-level architecture, and a discussion of this architecture. | Dependent on collaboration | Implement Vahid's suggestions of providing more content and description of tasks | Continue working on implementing the craterstats program with error handling. | The demo recreates the demo files no matter if they haven't been created and if they have then the demo doesn't create them again. The demo will leave the files on the system of the user | Include actual challenges the team has experienced in relation to our application development | Segragate plot file uploads to the application tool bar and data file uploads to the plot settings page | Make any recommended changes to the Software Testing Document's Introduction, Conclusion, and any additions to the testing parts. | Create a video and script for the prototype review of the design review 3. This video showcases all capabilities of the craterstats GUI | Now that we have solidified a style we add the content to the content blocks of our poster. | A draggable aspect of the graph to speciy which points to zoom in on | Add additional visuals of specific features of the GUI to highlight our key solutions. | Provide Trent with live demonstration, hardcopy deliverables, and sign off delivery check sheet.
[5 empty] | Actual Outcome: | N/A | Identical to Measurable | N/A | N/A | N/A | Current and future task content descriptions are improved and provide a clearer understanding | In progress | the GUI will check for the demo graphs on the system, if they're no there it makes them, otherwise nothing. | Present difficulties of including the craterstats library and issues with programming the gui | The source files are uploaded from the browse button on the Plot Settings page while the plot configuration upload is contained within the tool bar under files. | Recommended changes have been implemented. | In Progress | Content added | In Progress | Isolated screenshots of tabs, toolbar, plot, and containerized settings. | Smooth meeting with a tour of USGS!
[5 empty] | Current Status: | In Progress | Completed | In Progress | In Progress | Cancelled | Completed / Noted | Completed | In Progress | Completed | Completed | Completed | In Progress | Done | In Progress | Completed | Completed
[5 empty] | Task Description: |  | Draft Software Design Document | Software Design Architectural Overview | Software Design Module and Interface Descriptions | Implement third function | Provide functionality to the GUI Application | Try using app in Ubuntu | Seperate open and browse functionalities | Edit and Export the Design Review 2 Presentation | Software Testing Plan Intro & Conclusion | Update Installation Markdown | Update Problem Statement for DR3 | Revise content inside blocks | Find a way to include the space industry in problem statement | Finished implementing new save and import file format | Write User Guide
[5 empty] | Assigned Team Member(s): |  | All | TBD | Evan, Levi, Caden | Ibrahim Hmood | Evan | Alden | Evan | Evan | Evan | Evan | Alden | Alden | Alden | Caden | Evan
[5 empty] | Start Date: |  | 2024-08-30 | 2024-09-09 | 2024-09-09 | 2024-09-20 | 2024-09-23 | 2024-10-06 | 2024-10-11 | 2024-10-21 | 2024-10-25 | 2024-11-05 | 2024-11-08 | 2024-11-08 | 2024-11-24 | 2024-11-18 | 2024-12-09
[5 empty] | End Date: |  | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-27 | 2024-09-30 | 2024-10-06 | 2024-10-27 | 2024-10-24 | 2024-11-05 | 2024-11-12 | 2024-11-11 | 2024-11-22 | 2024-11-25 | 2024-12-02 | 2024-12-10
[5 empty] | Measureable Outcome: |  | Description of software's overall architectural design. | Consists of two parts: an architectural diagram of your system's high-level architecture, and a discussion of this architecture. | For each module, provide a detailed design description consisting of a short natural-language description, a UML class diagram, a description of the public interface of the component | Dependent on collaboration | Provide functional computation and display of statistic analysis. | App loads and executes without interruption. | Change the open button to specifically open ".plt" files and the browse button to open any type of data file (.stat, .diam, or .scc) | Edit all of the videos of presenters and images of slides to create a video presentation | brief paragraph summarizing the motivations, nature and primary goals of your application | Once the CraterstatsGUI is configured for pip installation, update the Windows markdown guide to enable the user to pip install our application | The problem statement has all the content needed and shared information in an effective way | Take the content made by teamates and condence the informaion into the format of the poster | The space industry has a great steak in astrogeology. It is important ot include it | New functions to read in .cs files and save .cs files to the format of Craterstats 3 | Develop a user guide for installing and operating the application.
[5 empty] | Actual Outcome: |  | N/A | N/A | In Progress | N/A | Call the craterstats cli application using the subprocess python library. Grab the plot image from the assets folder and display within the GUI | Application produces window error | In Progress | A professionally formatted video consisting of presentation slides filling the full frame, and video of team members in the bottom right corner. | An introduction properly introducing the document by providing the application's scope and then breifly describing the types of testing the document entails. A conclusion that breifly touches upon topics discussed within the document. | Installation and operation are separated between two markdown files. | Shortend the Problem statement to fit the time frame without loss of context from the original problem statemtent. | The content is as dense as possible while still delivering the most amount of information possible | Included space industry in problem statement. | New functions to read in .cs files and save .cs files to the format of Craterstats 3 | Write a markdown document going into depth the installation process for windows, mac, and linux. Also explain the user experience and I/O options.
[5 empty] | Current Status: |  | In Progress | In Progress | Completed | Cancelled | Completed | In Progress | In Progress | In Progress | Completed | Complete | Complete | done | done | Complete | Completed
[5 empty] | Task Description: |  | Discuss with Vahid his mentor - team communication requirements for the memo | Software Design Module and Interface Descriptions | Software Design Implementation Plan | Document what the cli.py Crater Stats functions do | Schedule Alpha Demo with Sponsor | Try using app in WSL | Change how files are read for new .plt format | Update Conclusion | Project Poster: Motivation Section | Address plot image export issue | DR3: Schedule | Convert the gimp file to Power point | Prepare the problem statement so it is ready for FEST | Rerecord video for prototype review to include new features | Fix pip installation
[5 empty] | Assigned Team Member(s): |  | All | TBD | Alden | Levi | Evan | Ibrahim | Caden | Levi | Levi | Caden | Levi | Alden | Alden | Caden | Ibrahim
[5 empty] | Start Date: |  | 2024-09-03 | 2024-09-09 | 2024-09-09 | 2024-09-22 | 2024-10-04 | 2024-10-07 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-11-05 | 2024-11-08 | 2024-11-08 | 2024-11-24 | 2024-11-20 | 2024-12-10
[5 empty] | End Date: |  | 2024-09-03 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-10-04 |  | 2024-10-27 | 2024-10-20 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2024-11-22 | 2024-11-27 | 2024-12-05 | 2024-12-11
[5 empty] | Measureable Outcome: |  | Explicitly stated standards provided by the Lunar Pit Patrol's team lead Vahid | For each module, provide a detailed design description consisting of a short natural-language description, a UML class diagram, a description of the public interface of the component | A design-centric implementation timeline for your project; Include a graphical display, such as a Gantt chart | The team will be able to know which CLI functions correlate to which button or menu in our GUI. Will work as a guide when we start plugging in functions | As Trent returns from his trip on October 3rd, we need to schedule a meeting with him and his associate Marc to acquire feedback on the alpha version of our capstone project. | Application executes without issue and manages plot generation and directory accessing correctly. | Change how files are being read to adhere to the new format and allow for data to be read correctly | Read the feedback from other groups and use that to make a new conclusion | Write the section explaining motivation behind developing Crater Stats | There is an issue where the plot image will not export if the file type is written along with the name by the user. | Create the Schedule portion of the design review 3 | Come up with a way to convert the poster image to power point for delivery | Fest is coming and we need to fill time. I can include more detail on the problem statement. | A new protoype review video that inlcudes the ability to create an overplot and the new command line | Theres an issue where craterstats can't find the 'Alpha' folder. Fix it.
[5 empty] | Actual Outcome: |  | Standards clearly stated in Discord | In Progress | N/A | A google doc with a list of the CLI functions and what they do | Schedule a meeting with Trent | Program should execute properly without issue when running in Linux | In Progress | Completion of the conclusion slide and script for DR2 | A complete motivation section of the final poster | No matter the end of file name the file gets exported as a PNG | one minute worth of content | Export image to PNG format and import into powerpoint as the same dimentions | More detail included inside of the problem statement | A new protoype review video that inlcudes the ability to create an overplot and the new command line | Craterstats is fully pip installable
[5 empty] | Current Status: |  | Completed | Completed | Completed | Completed | Upcoming | In progress | In Progress | Completed | In Progress | In Progress | Completed | Done | Progress | Complete | Completed
[5 empty] | Task Description: |  |  | Software Design Implementation Plan | Conclusion |  | Attempt import implementation | Create Plot to be always visible | Create Problem statement section | Modify GANTT chart | Project Poster: Challenges Section | Address Range input problem | DR3: Conclusion | Update file read and save functions |  | Update Changes to Challenges and Testing to past tense
[5 empty] | Assigned Team Member(s): |  |  | TBD | Levi |  | Caden | Caden | Alden | Levi | Levi | Caden | Levi | Caden |  | Evan Palmisano
[5 empty] | Start Date: |  |  | 2024-09-09 | 2024-09-09 |  | 2024-09-27 | 2024-10-07 | 2024-10-10 | 2024-10-18 | 2024-10-25 | 2024-11-05 | 2024-11-08 | 2024-11-11 |  | 2024-11-26
[5 empty] | End Date: |  |  | 2024-09-20 | 2024-09-20 |  | 2024-10-12 | 2024-10-25 | 2024-10-13 | 2024-10-20 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2024-11-15 |  | 2024-12-04
[5 empty] | Measureable Outcome: |  |  | A design-centric implementation timeline for your project; Include a graphical display, such as a Gantt chart | Overview of the document topics discussed. |  | A working prototype of the craterstats program by importing the current craterstats program rather than using the python subprocess library | Update GUI to have plot constantly on page and to refresh on button press or automatically. | Create problem statement for the video presentation | Use the feedback from the class presentation to modify the Gantt chart to be more presentable | Write the section detailing the various challenges the team experienced while developing the app | Fix the bug Trent brought up about range not display when the first number is not zero | Create the Conclusion for the design review 3 presentation | Update read file and save file functions to read in and save new .cs file format |  | Change the diction of the slide content to past tense to fit with the timeframe of our project
[5 empty] | Actual Outcome: |  |  | N/A | N/A |  | A working prototype of the craterstats program by importing the current craterstats program rather than using the python subprocess library | Updated GUI to have the plot image always shown on the GUi with the command line string always shown on the bottom. It is updated on change of function | Problem statement created | A new Gantt chart with a larger font and a few less necessary milestones we've completed to make things more readable | A complete challenges section of the final poster | Added error handling to let user know when input is not in range for the data that is plotted | one minute of content for the presentation | New read and save file functions to read and save in new .cs file format |  | Sentences describing previous challenegs and testing implementations to past tense.
[5 empty] | Current Status: |  |  | In Progress | Completed |  | Completed | Completed | Completed | Completed | In Progress | Completed | Completed | Completed |  | Completed
[5 empty] | Task Description: |  |  | Team Meeting | Team Meeting |  |  | Make demo | Present problem statement slides for draft | Update Implementation Overview | Plan poster presentaion details | Add details to artchitecture section on poster | Design Review 3 Challenges | Add functionality to program for click on graph |  | Implement pip installation
[5 empty] | Assigned Team Member(s): |  |  | All | All |  |  | Caden | Alden | Caden | Alden | Caden | Evan | Caden |  | Ibrahim
[5 empty] | Start Date: |  |  | 2024-09-13 | 2024-09-20 |  |  | 2024-10-07 | 2024-10-14 | 2024-10-18 | 2024-10-24 | 2024-11-05 | 2024-11-10 | 2024-11-18 |  | 2024-12-02
[5 empty] | End Date: |  |  | 2024-09-13 | 2024-09-20 |  |  | 2024-10-25 | 2024-10-14 | 2024-10-21 | 2024-11-01 | 2024-11-12 | 2024-11-14 | 2024-12-05 |  | 2024-12-12
[5 empty] | Measureable Outcome: |  |  | Meet as a team to dicuss upcoming assignment due dates, current project successes and issues, and other topics relevant to the team. | Meet as a team to dicuss upcoming assignment due dates, current project successes and issues, and other topics relevant to the team. |  |  | Create a button or ability in current program to create plots such as current program would is running craterstats -demo | Present the problem statement of the slides | Create multiple slides highligting key features and additions of the GUI and present content for design review 2 | Decide our content to display. Decide what style we want to use. What software we want to use to edit. (Powerpoint, GIMP, ect...) | Section of poster filled out with Architecture information | Update design review 2 challenges to resolved in design review 3. Present new challenges that have appeared due to testing. | Add functionality for users to click on section of the graph and have the graph zoom in onto that section |  | Configure GUI to be pip installable to improve ease of installation.
[5 empty] | Actual Outcome: |  |  | N/A | N/A |  |  | Utility button to recreate craterstats -demo function from the CLI program. Creates a Carousel of all plot images and command for corresponding image | Complete the presentation | Thurough explanation of the program's design implementation. | We chose gimp as our poster medium | Data has not yet been added | Go into depth about dr2 challenge resolutions, and talk about minor challenges from github issues such as sub plot combination and application crashes. | In Progress |  | Made CraterStats pip installable, have to work on fix
[5 empty] | Current Status: |  |  | Completed | Upcoming |  |  | Completed | Completed | Completed | Completed | Complete | In Progress | In Progress |  | Complete
[5 empty] | Task Description: | [5 empty] | Complete "Our Solution" and "Conflicts and Resolutions" for Design Review Presentation | Add functionality to the export button | Present the introduction for design review 2 | Record Live demo of GUI | Testing Doocumentation: Unit test | Project Poster: Motivation | Refactor subplots to be overplots
[5 empty] | Assigned Team Member(s): | [5 empty] | Ibrahim | Evan | Evan | Caden | Alden | Levi | Caden
[5 empty] | Start Date: | [5 empty] | 2024-10-10 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-24 | 2024-10-24 | 2024-11-11
[5 empty] | End Date: | [5 empty] | 2024-10-15 | 2024-10-12 | 2024-10-14 | 2024-10-21 | 2024-11-08 | 2024-11-08 | 2024-11-15
[5 empty] | Measureable Outcome: | [5 empty] | Create slides that go over our solution and conflicts we have faced, discuss in presentation | Create a function that allows the user to export a generated image to a user specified directory | Present the beginning slide, team introduction, and sponsor introduction for the design review video | A video of a live demonstration for the craterstats GUi application | Create unit tests for application | Write up the motivation for creating the Crater Stats GUI application | Refactor GUI feature to show all plot configurations within the graph rather than seperate graphs
[5 empty] | Actual Outcome: | [5 empty] | 4-6 additional slides over our solution and conflicts and resolutions. | Properly exports most recently generated image in png format to a user specified directory | 45 second long introduction clip | A video of a live demonstration for the craterstats GUi application |  | Enough content to fill in the motivation portion of the poster | In Progress
[5 empty] | Current Status: | [5 empty] | Completed | Completed | Completed | Completed | Completed | In Progress | In Progress
[5 empty] | Task Description: | [7 empty] | Edit and export the rough draft for design review 2 | Continue working on app improvements | Poster Fine detail design | Project Poster: Challenges | Address GUI Crashes
[5 empty] | Assigned Team Member(s): | [7 empty] | Evan | Caden, Levi, & Evan | Alden | Levi | Evan
[5 empty] | Start Date: | [7 empty] | 2024-10-14 | 2024-10-10 | 2024-10-25 | 2024-10-24 | 2024-11-04
[5 empty] | End Date: | [7 empty] | 2024-10-15 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-18
[5 empty] | Measureable Outcome: | [7 empty] | A well put together video consisting of presentation slides and team members presenting their respective topics | Continue improving the app to intake data points, reuse demos within a session, and differentiate plt and data files | Fine tune the elements of the poster to be eye catching while delivering the information in the most effective way | Write up the challenges that the team has faced throughout the dev process | Conduct tests using python scripts to run the application with a varying amount of plot generation to find a correlation in crashes and plot image count.
[5 empty] | Actual Outcome: | [5 empty] | 2024-10-10: A professionally formatted video consisting of presentation slides filling the full frame, and video of team members in the bottom right corner with the green screen background removed.; 2024-10-18: The changes are currently a work in progress; 2024-11-05: Enough content to fill in the challenges portion of the poster; 2024-11-08: Currently testing the GUI application and recording the results by timing the closing function and writing the number of plot images generated.
[5 empty] | Current Status: | [7 empty] | Completed | In Progress | Completed | In Progress | Completed
[5 empty] | Task Description: | [5 empty] | 2024-10-10: Design Review 2 Schedule; 2024-10-18: DR2 Project Schedule Update; 2024-10-25: Project Poster: Future Work Section; 2024-11-08: DR3 Testing Plan | DR3 Solution Overview | DR3 Solution Overview Update
[5 empty] | Assigned Team Member(s): | [5 empty] | 2024-10-10: Levi; 2024-10-18: Levi; 2024-10-25: Ibrahim; 2024-11-08: Evan | Ibrahim | Ibrahim
[5 empty] | Start Date: | [5 empty] | 2024-10-10: 2024-10-11; 2024-10-18: 2024-10-18; 2024-10-25: 2024-10-29; 2024-11-08: 2024-11-10 | 2024-11-20 | 2024-11-29
[5 empty] | End Date: | [5 empty] | 2024-10-10: 2024-10-14; 2024-10-18: 2024-10-20; 2024-10-25: 2024-11-05; 2024-11-08: 2024-11-14 | 2024-11-25 | 2024-11-29
[5 empty] | Measureable Outcome: | [5 empty] | 2024-10-10: slide created for the design review presentation; 2024-10-18: Read the feedback from the other teams and use that to make modifications to the schedule presentation; 2024-10-25: Write the section going over future features.; 2024-11-08: Introduce testing plan | Create new solution overview for design review 3 | Update the solution overview in design review 3: use past tense and emphasize plot view importance
[5 empty] | Actual Outcome: | [5 empty] | 2024-10-10: Ready to present the slide for the DR2 video; 2024-10-18: A new project schedule segment ready to be presented; 2024-10-25: Completion of future work section; 2024-11-08: Content is created, working on graphic for overall plan. | Created solution overview, continuing to work on it | Updated solution overview by emphasizing importance of plot view and using past tense
[5 empty] | Current Status: | [5 empty] | 2024-10-10: Completed; 2024-10-18: Completed; 2024-10-25: In Progress; 2024-11-08: Completed | Completed | Completed
[5 empty] | Task Description: | [5 empty] | 2024-10-10: Design Review 2 Conclusion; 2024-10-18: Update and present Solution Overview; 2024-10-25: Software Testing Plan Integration Testing
[5 empty] | Assigned Team Member(s): | [5 empty] | 2024-10-10: Levi; 2024-10-18: Ibrahim; 2024-10-25: Caden & Evan
[5 empty] | Start Date: | [5 empty] | 2024-10-10: 2024-10-11; 2024-10-18: 2024-10-20; 2024-10-25: 2024-10-24
[5 empty] | End Date: | [5 empty] | 2024-10-10: 2024-10-14; 2024-10-18: 2024-10-21; 2024-10-25: 2024-11-08
[5 empty] | Measureable Outcome: | [5 empty] | 2024-10-10: slide created for the design review presentation; 2024-10-18: Create a new solution overview slide and present it. Be sure to practice.; 2024-10-25: 2-3 pages of detailed analysis and explanation of integration testing implemented for our program
[5 empty] | Actual Outcome: | [5 empty] | 2024-10-10: Ready to present the slide for the DR2 intro.; 2024-10-18: A new solution overview slide and presentation.; 2024-10-25: 3 pages of detailed analysis and explanation of integration testing implemented for our program
[5 empty] | Current Status: | [5 empty] | 2024-10-10: Completed; 2024-10-18: Completed; 2024-10-25: Completed
[5 empty] | Task Description: | [5 empty] | 2024-10-10: Design Review 2 Implementation Solution; 2024-10-25: Create infographic for implemented techonologies on poster
[5 empty] | Assigned Team Member(s): | [5 empty] | 2024-10-10: Caden; 2024-10-25: Caden
[5 empty] | Start Date: | [5 empty] | 2024-10-10: 2024-10-11; 2024-10-25: 2024-11-01
[5 empty] | End Date: | [5 empty] | 2024-10-10: 2024-10-14; 2024-10-25: 2024-11-01
[5 empty] | Measureable Outcome: | [5 empty] | 2024-10-25: An infographic showing the two technologies used when creating craterstats,
[5 empty] | Actual Outcome: | [5 empty] | 2024-10-25: An infographic showing the two technologies used when creating craterstats,
|  |  |  | Current Status: | [6 empty] | 2024-10-25: Completed
[5 empty] | Task Description: | [5 empty] | 2024-10-10: Completed solution overview for design review 3; 2024-10-25: Poster artistic details
[5 empty] | Assigned Team Member(s): | [5 empty] | 2024-10-10: Ibrahim; 2024-10-25: Alden
[5 empty] | Start Date: | [5 empty] | 2024-10-10: 2024-11-11; 2024-10-25: 2024-11-01
[5 empty] | End Date: | [5 empty] | 2024-10-10: 2024-11-11; 2024-10-25: 2024-11-15
[5 empty] | Measureable Outcome: | [5 empty] | 2024-10-10: Completed design review 3 solution overview; 2024-10-25: Make poster eye catching while still delivering information as effectively as possible.
[5 empty] | Actual Outcome: | [5 empty] | 2024-10-10: Ready to present
|  |  |  | Current Status: | [6 empty] | 2024-10-10: Complete; 2024-10-25: Completed
Task Description:
Assigned Team Member(s):
Start Date:
End Date:
Measureable Outcome:
Actual Outcome:
Current Status:
Task Description:
Assigned Team Member(s):
Start Date:
End Date:
Measureable Outcome:
Actual Outcome:
Current Status: